## DTT Test Hour Log
Instruction: Fill in the number of hours that were required to complete the test. Please include every step you took during the process and include a detailed description of every step. Add reasoning on why you took certain decisions or applied specific techniques. We prefer quality over quantity so take your time with the test and the log.
Subject | Amount of hours | Date | Description | Bonus
Set the configuration and base style | 1 | 2023-07-12 | Set configuration including Pinia, commitlint, husky, eslint and prettier. Remove boilerplate code and add the base styles for the project as the colors.
Story 1 - Create the header | 2 | 2023-07-12 | Create a navigation header with two router-link(for houses and about pages) and a component 'BaseWidth' to set the maximum width of the content.
Story 2 - Create a house card and fetch available houses from server | 4 | 2023-07-13 | Create a house card component using a grid template and use it to render the lists of the house. Made the fetch of houses on the server and a v-for to loop over the response and render the houses on the page. It was noticed that in the project design, the numbers were with a thousand separators, and the backend didn't return the number in this format. So, the treatment of the price is made in a function.
Story 3- Create buttons to sort by price and size, input field to search houses by city and a button to create a new house | 2 | 2023-07-14 | Create a HouseNav component to host the options to search, sort and create a new house.
Story 3- Allow users to search houses by city name | 4 | 2023-07-15 | Implement the logic to search houses by city in HouseNav component. The user can clear its search by clicking the clear icon inside the search bar or erasing the field. A HouseNotFound component was created to appear if no houses match the search.
Story 4- Allow user to sort the houses by price or size | 3 | 2023-07-16 | Implement the logic to sort houses by price or size and clear the sorting in HouseNav component.
Story 5- Create a house detail view | 4 | 16/072023 | Create the style for the HouseDetails page. It was decided to make two child components for this, one for the house image detail and the other for the description, both to be hosted in the HouseDetails component view. This was decided to make it easy the style transition to mobile view.
Add a state management (Pinia) file for track houses | 2 | 2023-07-17 | At this point, it was noticed the necessity of a state management for the project, so it was created using Pinia. The HousesStore was created to contain actions to be used through the application regarding changes in houses data, such as edit, delete, and fetch. So in this way, a sync between the application and the server is made in a more appropriate way.
Story 5- Allow user to go to the details page of a specific house clicked | 3 | 18/072023 | The id of the selected house is passed to the details page as a parameter through router, and use it there to make the fetch by id. It was created a composable folder to host the formatPrice function, so it can be used in any place in the app, avoiding repetition. A check is made in the store to see if the house selected already exists in the store, so there is no need to make a request to the server.
Story 6- Create a form to the user post a new house | 3 | 2023-07-19 | Create the form style so the user can post a house. It was noticed the repetition of 'Back to overview' button, so it was created a separeted component to be reused in form's page and details' page.
Story 6- Allow user to post a new house | 4 | 2023-07-21 | At this point, the form inputs were split into a different component, thinking it would be a better manner to manage the form (I was wrong). Start to use async/await in the store management.
Story 7- Add an edit and delete button on the houses that the user owns | 2 | 2023-07-21 | Create a component to host these buttons as they are used in more than a component.
Story 8- Allow the user to edit his house | 4 | 2023-07-22 | Changed all the actions in store management to async/await format. Create an action to update the houses in sotre when user edit a house, by replacing the previous one. Add edit logic and redirect the user to the details page if everything goes well.
Story 9- Create the desktop view for delete a house | 3 | 2023-07-22 | Created a base card component hosting the standard style of the cards used in the application and apply to other components. Also, a base modal was created to be used in the delete house modal. Add the logic to delete a house from the server and from the store.
Refactoration and fixes | 4 | 2023-07-23 | Create and apply in the application a reusable BaseButton and SearchBar components. Made a big refactoration in HouseForm as it was noticed that the split into a formInput component was dificult to maintain, not reusable and more complex than what should be. Fix typos. Add validations in the template of the form. Create a HouseFilter component.
Add an About Page | 2 | 2023-07-24 | Add an about page to the component already created. | x
Refactoration and fixes | 3 | 2023-07-24 | Fix the header in mobile view and size down icons. Refactor state management to use async/await. Refactor 'BackTo' component to use BaseButton so it is more reusable as well. Fix minor issues in HouseForm, HouseDetails and BaseButton. Create a PageNotFound for a non-existent router
Refactoration and fixes | 4 | 2023-07-25 | Apply SCSS in all application since it is more easy to handle the styles. Add documentation. Refactor folder structure. Create the missing mobile view to the HouseDelete. Refactor DetailImage. Fix minor errors in style.
Allow users to filter houses created by them | 2 | 2023-07-26 | Create a button in HouseFilter to user also be able to filter their own houses, also in sync with filter by city or sort options | x
Total amount of hours | 52